**Ministry Allocation Fund (MAF) Grant**

**Congregational Growth and Ministry Resources**

**Projects Evaluation and Monitoring Group (PEMG) - Process Overview**

The objectives of the PEMG project methodology include:

* Ensuring the best chance of success using proven project management practices;
* Ensuring parishes and Diocesan committees have a clear process which is easy to use and understand;
* Ensuring appropriate stewardship over MAF legacy funds;
* Ensuring appropriate diligence for the investments involved; and,
* Including safeguards which embrace lessons learned from past projects.

You may feel that your parish is not ready to undertake a major MAF funded project. Before you start, review the Task Check-list to better understand what will be required. If you decide to proceed, the chart below will help you understand how the process will progress.

|  |
| --- |
| **PROJECT FEASIBILITY** |
|  | **Process Flow** |  |
| **Objectives** |  | **DISCUSS YOUR PROJECT IDEA WITH YOUR AREA BISHOP** **This will determine if your** **idea has merit.** |
|  | ↓ |  |
|  | Have a conversation with Diocesan Staff416-363-6021 or 1-800-668-8932 ext. 225 | This will determine whether the idea is in scope; in the right funding stream; in alignment with mission strategy and/or sustainability, etc. |
| Feasibility, Timing, Area Strategy, Parish Situation, Issues/background | Speak with your Area Bishop | Book a meeting or telephone call with your Area Bishop. This will determine whether or not you proceed with preparing a Project Feasibility Report |
|  | ↓ |  |
| Opportunity Identification,Self-Sufficiency Scenario,Proposal Team/Timing | Prepare Project Feasibility Report | By the Parish Team using the Project Feasibility Report **Template** |
|  | ↓ |  |
| Assumptions Confirmed | PEMG/Staff review,Area Bishop approval to proceed | Okay to proceed with Proposal preparation; copy to PEMG members |
|  | ↓ |  |
| Experts at the Table,Right the First Time,Ensure Consistency | PEMG Volunteer Coach assigned | Introduction by phone or email, send samples to Parish Team, Schedule Workshop to develop Proposal |
|  | ↓ |  |
| Content Insured,Parish Team Built,Issues Resolved | Proposal Workshop(in parish) | 1 to 2 days, facilitated by PEMG coach |
|  | ↓ |  |
| Third Party Assessment,Success Rating Established,Area Bishop Buy-in | Risk Assessment (coach)Diocesan Staff obtains Area Bishop approval/sign off | Draft Proposal and Risk Assessment to PEMG by email; All member feedback/support;Copies to Area Bishop |
|  | ↓ |  |
| Executive Board Buy-In/Support | **Executive Board Review**(Recommendation to Diocesan Council) | Area Bishop and Parish Team Presents to Executive Board;Proposal and Risk Assessment circulated in advance of the meetingIf recommended, copies of the documentation will be circulated to Diocesan Council |
|  | ↓ |  |
| Diocesan Council Buy-In/Support | **Diocesan Council Review** | Proposal Approved,if majority supported |

|  |
| --- |
| **PROJECT EXECUTION** |
| **Objectives** | **Process Flow** |  |
| Team Formation,Task Assignments,Monitoring Process in Place | Project Kick-Off(parish Transition Manager) | Review of Implementation Plan;Task Assignments; Reporting |
|  | ↓ |  |
| Tasks Executed,Status Meetings Held, | Execution to Plan | Transition Manager Tracks Progress,**Quarterly/Semi-Annual/Annual Reporting** to PEMG coach & Area Bishop; copies will be circulated to PEMG |
| Issues Resolved;Plan Revised | ↓ |  |
|  | MAF Grant Installments(Payments) | Grant Installments Authorized by the Director of Congregational Development based on PEMG okay, **Quarterly/Semi-Annual/Annual Reporting as mandated by** **Diocesan Council**Annual Report Summary Submitted to Diocesan Council |
|  | ↓ |  |
| Improve Process | Project Closeout | **Project Completion Report**Prepared with PEMG Coach; Includes Lessons Learned;Tips for other Parishes**Final Report to Diocesan Council** |